## OIG Overview
OIG Name: | General Services Administration
OIG Broad Recovery Act Goals: | The overall objectives of the IG’s oversight of the Recovery Act funds are to ensure timely and effective implementation of stimulus related activities, proper internal control procedures are established and maintained, and to prevent and detect fraud, waste, and abuse.
OIG Broad Outreach Recovery Act Goals: | The Office of Inspector General will be providing targeted fraud awareness briefings to GSA personnel who will be assigned to carry out GSA's activities under the Recovery Act. These briefings will serve to heighten awareness of fraud indicators and to discuss past and potential fraud schemes. Provided to groups of GSA employees and contractors, these briefings will serve as an educational tool and aid in preventing fraud, waste, and abuse.
OIG Recovery Act Risk Assessment Process: | Risk assessments for both programs were completed using the accountability objectives in OMB's Recovery Act Impementaion Guidance as a basis. In performing the analysis, we utilized the Recovery Act, draft agency program plans, agency spending plans, internal control guidance developed by COSO, as well as internal knowledge of both programs developed through past audit work. Based on the risk assessments, risk ratings were assigned to the programs. Using the risk assessments as a guide, oversight of the agency's programs will place more emphasis on the high risk program, although the medium risk program will also be subject to review. The oversight will include monitoring of program activities, reviews of projects at multiples stages, and program reviews. The OIG will also implement a fraud awareness program to educateAgency personnel and contractors regarding fraud schemes and how to report suspected fraud.
OIG Recovery Act Funds: | 7000000
Expiration Date of OIG Recovery Act Funds: | 2013-09-30
FY 2009 OIG Non-Recovery Act Funds: | 54000000
Number of OIG Planned Recovery Act Hires: | To date we have redeployed experienced staff to Recovery Act oversight. A dual compensation waiver authority delegation will be used to hire annuitants. New hires have not been specifically assigned to the Recovery Act oversight.
OIG Recovery Act Funds to be Allocated to Contracts: | 0
Purpose of Recovery Act Contracts: | To obtain specialized expertise for audits/reviews, and evaluations lead by OIG staff. No contracts are expected in FY 2009.
Types of Recovery Act Contracts Awarded to Date: | No contracts have been awarded to date.
Link to OIG FY 2009 Recovery Act Work Plan: | The Recovery Act Work Plan is under development and has not been approved for release yet.

## Work Plan
Agency | Program Area | Agency Recovery Act Funds Associated w/Program Area | Type of Review (Administrative / Financial, Eligibility, Performance, Other) | Entity Performing Review (OIG Staff, Contractor, Other) | Project Title | Background | Objective | Expected Quarter in Which Work will Start | Expected Quarter in which Final Report will be Issued | Expected Number of Reports | Entity Performing Review
GSA | High Efficiency Vehicels | 300000000 | Performance | OIG Staff | Recovery Act: Purchase of Vehicles | Recovery Act provided funding to acquire motor vehicles with higher fuel economy with funds expiring on September 30, 2011. | Ensure program is run efficiently and effectively. | FY 09, 3rd |  | 1 | OIG Staff
GSA | Federal Buildings Fund | 4200000000 | Performance | OIG Staff | Recovery Act: Major Construction Projects | The Recovery Act provided GSA with $5.55 billion in construction funds. Approximately $4.2 billion will be used for major construction projects including new Federal Buildings, Courthouses, and Land Ports of Entry; as well as for measures to convert GSA facilities to High Performance Green Buildings. | Ensure GSA's Recovery Act funding is used to meet Recovery Act program goals and accountability objectives. | FY 09, 3rd |  | multiple | Contractor
GSA | Federal Buildings Fund | 1000000000 | Performance | OIG Staff | Recovery Act: Limited Scope and Small Projects | The Recovery Act provided GSA with $4.5 billion for measures to convert GSA facilities to High Performance Green Buildings. GSA will use about $1 billion of that funding on limited scope and small building projects. | Ensure GSA's Recovery Act funding is used to meet Recovery Act program goals and accountability objectives. | FY 09, 3rd |  | multiple
GSA | Federal Buildings Fund | 0 | Performance | OIG Staff | Recovery Act: Reimbursable Work Authorizations | Customer agencies have received over $1 billion in Recovery Act funding for construction that GSA will carry out. | Ensure customer funding is used to meet Recovery Act program goals and accountability objectives. | FY 09, 3rd |  | multiple | Other
GSA | Fraud Awareness | 0 | Other | OIG Staff | Recovery Act: Fraud Awareness Briefings | GSA OIG and DOJ staff will provide fraud awareness briefings to GSA personnel. GSA OIG will also provide fraud alert memoranda to the agency as needed. | Ensure GSA personnel are aware of and alert to potential fraud, waste, and abuse. | FY 09, 3rd |  | none
GSA | Federal Buildings Fund | 450000000 | Administrative/Financial/Performance | OIG Staff | DHS Headquarters Project | The DHS HQ construction project is estimated at $3.4 billion. The Recovery Act provided $450 million for GSA and $200 million to DHS for the project. | Ensure GSA's and DHS's Recovery Act funding is used to meet Recovery Act program goals and accountability objectives. | FY 09, 3rd |  | multiple
Type of Reviews
Administrative/Financial Reviews - reviews of management administrative issues, management internal controls, or financial systems/processes
Eligibility Reviews - reviews to determine if eligibility requiremetns were met for a given program
Performance Reviews - reviews to determine the effectiveness of a given program
Other Reviews - reviews that do not fit within the above categories